## Plan
Second Draft — scope and plan
What is built, what launch needs, and what can wait.
Item | What it means | Status | Who
LIVE NOW
Room studio | Upload a room, pick a look (or write a brief), get redesigns back | Done | Aishika
Keeps what matters | Doors, windows, built-ins and ticked furniture stay where they are | Done | Aishika
Every angle redrawn | A full redesign takes 2+ photos and returns each one redesigned, matching | Done | Aishika
Compare, download, edit | Before/after slider, downloads, and follow-up changes to a design | Done | Aishika
Talk it through | Chat with a designer assistant about the design on screen | Done | Aishika
Accounts & history | Email sign-up, saved designs, past rooms | Done | Aishika
Cost estimate | Indicative cost per room, in AED at local rates | Done | Aishika
Plans | Free / One Room / Whole Home / Studio change quality and number of designs | Done | Aishika
WhatsApp handover | 'Talk to a designer' under finished designs opens a chat with you | Done — needs your number | Both
TO LAUNCH
Google sign-in | Needs a Google Cloud project and a one-time Google review | To do | Both
Paid hosting | Site and database off the free plan (free database is deleted after 30 days) | To do | Aishika
Domain | Buy and connect the web address | To do | Both
Free-plan daily limit | Stops anyone running up the image bill | To do | Aishika
Privacy policy & terms | Includes a line that designs are a visual aid, not a site survey | To do | Both
SEO basics | Page titles, descriptions, sitemap, Google Search Console | To do | Aishika
Error alerts | Get told when something breaks, before a client does | To do | Aishika
Real-room testing | 5–10 real homes through it before going public | To do | Both
DECIDE
Sell plans, or free lead tool? | If the goal is enquiries, the studio can be free (with a daily limit) and payments aren't needed at all | Your call | Eleganza
Catalogue | Only worth doing with real product photos, sizes and prices — otherwise park it | Your call | Eleganza
LATER (IF WANTED)
Stripe payments | Charge for plans in AED — only if you sell plans | Later | Aishika
Product catalogue live | Designs steered toward pieces you actually supply | Later | Both
Usage dashboard | See designs made, enquiries and cost without asking | Later | Aishika
Arabic | Arabic version of the site | Later | Aishika

## Costs
Running costs
Everything the site costs to run, and who pays for it. Blue: published prices (see notes). Green: pulled from 'Per design'.
USD → AED | 3.6725
Item | What it's for | How it's billed | Cost (USD) | Per | Monthly (USD) | Monthly (AED) | Paid by | Notes
Hosting — website | Keeps the site awake and on your own address | Fixed | 7 | month | 7 | 25.7075 | Aishika — added to invoice | Render Starter. The free plan sleeps after 15 min, so the next visitor waits about a minute.
Hosting — database | Accounts and saved designs | Fixed | 6 | month | 6 | 22.035 | Aishika — added to invoice | Render Basic-256mb. The free database is deleted 30 days after it is created, data and all.
Domain | Your web address | Fixed | 34 | year | 2.8333 | 10.4054 | Eleganza | A .ae is about AED 125/yr and needs no trade licence (.co.ae does). A .com is cheaper, ~$10–15/yr. Register it in Eleganza's name.
Image & reading (OpenAI) | Every design and room reading | Per use | 41.26 | month | 41.26 | 151.5274 | Eleganza — on your card | Depends entirely on how many people use it. Example usage on the 'Per design' tab.
Payments (Stripe) | Taking money for paid plans | 2.9% + AED 1 per sale |  | per sale | 0 | 0 | Eleganza | No monthly fee. +1.5% on international cards. Only needed if you sell plans.
WhatsApp button | 'Talk to a designer' after a design | Free | 0 | month | 0 | 0 | — | Opens a chat with your existing WhatsApp Business number. No API or fees.
Google sign-in | Sign in with Google | Free | 0 | month | 0 | 0 | — | Needs a privacy policy page and a one-time Google review.
SEO basics | Being found on Google | Free | 0 | month | 0 | 0 | — | Search Console, sitemap, Google Business Profile link. Ads or an agency are optional and separate.
Error alerts | Know when something breaks | Free | 0 | month | 0 | 0 | — | Sentry free plan.
Fixed each month (hosting + domain) |  |  |  |  | 15.8333 | 58.1479
Total each month, with example usage |  |  |  |  | 57.0933 | 209.6753
Build (one-time, design and development) | As agreed between us — separate from the running costs above.
Note on B4: The dirham is pegged to the US dollar at 3.6725.
Note on D7: Source: Render pricing, Starter web service $7/month (checkthat.ai/brands/render/pricing, Sep 2026).
Note on D8: Source: Render Postgres, Basic-256mb $6/month; free instances expire after 30 days (render.com/docs/postgresql-refresh, Sep 2026).
Note on D9: Source: .ae registration from AED 125/yr (cybernews.com/best-domain-registrars/best-ae-domain-registrars, Sep 2026).
Note on D11: Source: stripe.com/ae/pricing — 2.9% + AED 1 per successful card charge (Sep 2026).

## Per design
What each design run costs
Yellow cells: change these to your expected usage. Blue: prices (sources in the cell notes).
Image price by quality (USD, per image)
medium | 0.042
high | 0.167
xhigh | 0.25
Reading a room (per run) | 0.01
USD → AED | 3.6725
Plan | Quality | Designs per run | Cost per design (USD) | Cost per run (USD) | Cost per run (AED) | Runs per month | Monthly (USD) | Monthly (AED)
Free | medium | 2 | 0.042 | 0.094 | 0.34521 | 150 | 14.1 | 51.7822
One Room | high | 3 | 0.167 | 0.511 | 1.8766 | 30 | 15.33 | 56.2994
Whole Home | high | 4 | 0.167 | 0.678 | 2.49 | 10 | 6.78 | 24.8996
Studio | xhigh | 4 | 0.25 | 1.01 | 3.7092 | 5 | 5.05 | 18.5461
Total | [5 empty] | 195 | 41.26 | 151.5274
A full redesign returns one design per photo, so 'Designs per run' is the most a plan allows. Runs per month are an example — replace with your own guess.
Note on B5: Source: OpenAI GPT-Image-1 pricing, 1024x1024 medium — developers.openai.com/api/docs/models/gpt-image-1 (Sep 2026).
Note on B6: Source: OpenAI GPT-Image-1 pricing, 1024x1024 high — developers.openai.com/api/docs/models/gpt-image-1 (Sep 2026).
Note on B7: Estimate: top of OpenAI's published GPT-Image-1 range ($0.011–$0.25). Confirm on the OpenAI usage page once live.
Note on B8: Estimate for one vision call that lists what is in the room and prices it. Confirm on the OpenAI usage page.

## Need from you
What I need from Eleganza
Status column: pick from the list as things come in.
# | What | Why | When | Status
1 | WhatsApp Business number | Turns on the 'Talk to a designer' button | To launch | Pending
2 | Who answers WhatsApp enquiries, and when | So people who tap it hear back | To launch | Pending
3 | Domain name choice | Your web address; registered in Eleganza's name | To launch | Pending
4 | Logo and brand colours | So the site looks like Eleganza | To launch | Pending
5 | 6–10 photos of finished projects | Real work on the home page builds trust | To launch | Pending
6 | Support email address | Site footer, and required by Google sign-in | To launch | Pending
7 | A Google account to own the sign-in setup | Google sign-in is created under your account | To launch | Pending
8 | OpenAI account on Eleganza's card | Designs are billed to you, not to me. Needs a one-time ID check with OpenAI | To launch | Pending
9 | Approve hosting (~$13 / AED 48 a month) | Website + database; I pay and add it to my invoice | To launch | Pending
10 | Sign-off on privacy policy & terms | I'll draft them; you approve | To launch | Pending
11 | Decision: sell plans, or free lead tool | Decides whether payments are needed at all | To launch | Pending
12 | Plan prices in AED | Only if selling plans | Later | Pending
13 | Stripe account (trade licence, UAE bank account) | Only if selling plans — Stripe signs up the business, not me | Later | Pending
14 | Catalogue: yes or no | If yes: photos, sizes in mm and AED prices, in the template I sent | Later | Pending